## ENG (hidden)
Capacity Development Plan - ASAP - Cote d'Ivoire
Organization | ASAPSU
Update | 2020-04-22
Capacity Area | Capacity Gap | Key Intervention | Sub-Intervention(s) | Expected Results | ASAP Indicator | Responsible | Timelime | [8 empty] | Status Report
[7 empty] | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Legal Structure
Financial Management and Internal Control | No adequate accounting bookkeping system | Acquire and implement an accounting software system that able to record, track, consolidate, and report on all financial transactions in a credible manner by funding source | Aquire and roll-out an accounting software | All financial planning, transactions recording and reporting are done using an adequate software | bar: Timelime Apr to Timelime May
|  |  | Develop a chart of accounts applicable to all projects and units | Financial statements are produced based on established chart of accounts and general ledger | bar: Timelime Apr to Timelime Jun
|  |  | Establish an accounting month/year closing process producing reliable financial statements | Reliable financial statements, including bank reconciliations, are performed monthly/annually | bar: Timelime May to Timelime Jul
| Finance & Admin structure designed for isolated projects and not adapted to support a multi-projects/units organization | Reinforce leadership on Finance and Administration | Recruit/Appoint a Finance (and Administration) Director for the entire organisation | Finance and Admin strategy and functions are supervised by a solid manager
|  |  | Define board control role on finance, budget & audit processes | Board reviews and approves annual budget and audited financial statements
|  | Initiate a finance planning, monitoring and control procedure | Establish a corporate budget cycle including all projects for the organisation | A consolidated annual budget is established for the organization based on projects/units budgets
|  |  | Design a cost share policy | Cost allocation prodedure is established and projects support a fair portion of costs | bar: Timelime Jun to Timelime Sep
|  |  | Design an indirect cost policy covering structural cost | Each project new proposal/project contribute to the structural cost | bar: Timelime Jun to Timelime Sep
| Existing finance manual is incomplete and weak | Update financial manual to include USG rules and regulations requirements | Ensure procedures take into account requirements from standard provisions, 2 CRF200 and other USG guidelines | Oganization financial manuals comply with USG regulations | bar: Timelime Jun to Timelime Sep
Procurement | Organization has incomplete and weak procurement procedures and management | Reinforce procurement procedures and policies and update forms and templates | Develop adapted procurement procedures, policies and forms | Oganization procurement manuals comply with USG regulations | bar: Timelime Jun to Timelime Sep
|  |  | Redefine staff role and contribution in procurement operations | Clear segregation of duty is estasblished reducing the risk of fraud
|  | Roll-out new procurement manual | Train staff on procurement best procedures and practices | Staff knows and applies procurement processes | bar: Timelime Aug to Timelime Sep
|  |  | Ensure new forms and templates are in place and used for all procurement operations | Purchase goods and services are operated using harmonized forms
Human Resources | Organization has incomplete and weak HR policies, procedures and practices | Reinforce policies regarding ethics | Code of conduct, conflict of interest, anti-harassment… to be further developped & rolled out | All staff are trained on different ethics themes and regularly sign related aknwolegment forms | bar: Timelime May to Timelime Jun
|  | Update Organogram to reflect present structure | Differenciate present and forecasted organograms | Vacant positions are clearly idenfy on organograms that represent present situation and future staffing | bar: Timelime May
| No established salary grid | Develop a salary grid defining remuneration package | Ensure salary determination for new staff and advancement is performed based on set criteria | Rules for salary determination and increase are known and objective | bar: Timelime Jun to Timelime Jul
| No adequate accounting payroll software | Acquire and roll out a payroll and HR management software | As much as possible, combine with accounting sofware | Staff contracting, vacation and remuneration are managed using a reliable software
| Timesheet are based on estimates worked time | Train staff on timesheet reporting requirements | Ensure timesheets reflects real worked plan and does not only duplicated apporved LOE by donor | Employee timesheets reflect executed work and are reviewed, approved and controlled | bar: Timelime Jun to Timelime Jul
| Staff files are scattered with weak confidentiality protection | Assist HR to ensure all personnel files are consolidated at one location. | Limit access to approved staff | Staff personal files are up-to-date, kept in a safe location with controlled access | bar: Timelime Jun
Project Performance Management
Organizational Sustainability | No accrual recorded for staff end of contact payment | Define and implement an accrual policy for staff termination payment | Ensure a fair share of staff termination payment is allocated to project costs | Sufficient funding is provisionned yearly to cover staff end of contract payment
| Organization management does not sufficicienty anticipate potential risks | Initiate risk management approach to orient strategy and operations | Design a risk analysis matrix | A risk assessment process is intergrated in yearly planning process | bar: Timelime May
|  |  | Proceed with Executive Directorate to risk analysis and encourage an adaptive strategy | Executive Management assess risks related to operations at least once a year
IT | No written IT policy and basic IT requirements not in place | Develop an IT policy | Define basis IT rules and processes | An IT policy is in place, explained to all staff and presented to new employees | bar: Timelime Jul to Timelime Aug
|  | Rollout IT policy and best practice guideline | Ensure all staff are instructed on IT processes and best practice | Data and equipment are secured, data is regularly backuped and recovery process is tested.
| IT operations are not coordinated | Create an IT department or function | Recruit/appoint an IT manager or hire external service provider to manage IT functions | IT strategy and functions are supervised by a solid manager
Internal Control & Audit Readiness | Organization has weak mechanisms to verify compliance with its own regulations. | Institute a control self assessment process and timeline | Design a control self assessment matrix based on organization manuals | A control self assessment tool is in place and endorsed by Executive Management | bar: Timelime Aug
|  |  | Encourage frequent compliance tests are performed internally by independant staff | Self assessment review is performed at least once a year | bar: Timelime Sep
| Organization does not perform audit to validate annual finance statements | Institute an audit process including a compliance review with local laws | Motivate audit requirements to be inserted in organization status | Organization status includes audit requirements. Audited financial reports reviewed by board
|  |  | Encourage yearly external audit to be performed for the entire organization by a recognized firm | Annual audit is undertaken evey year to measure compliance with local laws and donor requirements
Sub-Award and Grants Management | Existing sub-award procedures and processs are weak and may generate major risks | Develop a dedicated sub-award manual | Ensure new subaward manual clearly defines selection process and transfers legal responsability | Subaward manual is in developped and endorsed by Executive Management | bar: Timelime Aug to Timelime Sep
|  | Improve subward management | Adapt subaward agreements to include new requirements | Sub-recipients are aware of their responsabilities and comply with new regulation | bar: Timelime Aug to Timelime Sep
Note on B7: Finding or result of the assessment.
Note on C7: Main action guided by ASAP’s interventions
Note on D7: Sub-actions breaking the intervention into manageable sections
Note on E7: Expected change

## Instructions
INSTRUCTIONS
1 | The Capacity Development Plan is workplan based on the results of the NUPAS Plus.
2 | After NUPAS assessments are complete, transfer all scores that are 3.0 and below into column C in the next worksheet
3 | If there are USAID Special Award Condtions insert at the top of CDP. Ensure to include the deadlines specified by USAID.
4 | In a locally led process, complete the key activities sections of the CDP with recommended activities that will improve gaps identified in domains and their sub domain components.
5 | In a locally led process, complete the expected results. Reference tools and templates from to "Path to Prime" as starting points for final deliverables
6 | In a locally led process, identify organizational leads and capacity advisor assigned to subcategories.
7 | In a locally led process, obtain organizational leadership approval and commitment to implement.
8 | Request USAID's review and approval. Ensure the coutnry budget has sufficent funds to complete capacity strengthening activities
9 | Finalize CDP and include in the organization's and capacity advisor's workplan.
10 | The CDP is a living document and continues to be updated by the organization and capacity advisors with progress and emergent developments.
11 | Develop CDP 2 after reassessments to refocus activities and deliverables.

## CDP 1
ASAP II CAPACITY DEVELOPMENT PLAN
ORGANIZATON NAME
DATE OF UPDATE
DOMAIN AND CRITERIA |  | BASELINE SCORE | REASSESSMENT 1 | REASSESSMENT 2 | KEY ACTIVITIES | SUB ACTIVITIES | EXPECTED RESULTS | ORGANIZATIONAL LEAD | CAPACITY ADVISOR | TOOL USED OR DEVELOPED | START DATE | END DATE | ADD COLUMNS FOR MONTH OR QUARTERS | ORGANIZATION UPDATE | CAPACITY ADVISOR UPDATES | ASAP II INDICATOR
|  | Date: | Date: | Date:
SPECIAL AWARD CONDITIONS
1 |  | - | - | -
2 |  | - | - | -
3 |  | - | - | -
4 |  | - | - | -
5 |  | - | - | -
1. Legal
1.1 | Subawards | - | - | -
1.2 | Pre-Award Questionnaire | - | - | -
1.3 | Agreement | - | - | -
1.4 | Monitoring | - | - | -
1.5 | Audit | - | - | -
1.6 | Tracking | - | - | -
1.7 | Taxes | - | - | -
1.8 | Delegation of Authority | - | - | -
1.9 | Law suits | - | - | -
| Average Score | - | - | -
2. Finance
2.1 | Budget | - | - | -
2.2 | Cost Allocation | - | - | -
2.3 | Documentation | - | - | -
2.4 | Advance payments | - | - | -
2.5 | Petty Cash | - | - | -
2.6 | Budget Variance | - | - | -
2.7 | Cash Flow Budgets | - | - | -
2.8 | Accounting System | - | - | -
2.9 | Accounting Records | - | - | -
| Average Score | - | - | -
3. Fraud
3.1 | Policy | - | - | -
3.2 | Reporting | - | - | -
3.3 | Risk assessment | - | - | -
3.4 | Training | - | - | -
3.5 | Subawards | - | - | -
3.6 | Compliance | - | - | -
3.7 | Internal controls | - | - | -
| Average Score | - | - | -
4. Procurement and Logistics
4.1 | Approval Process | - | - | -
4.2 | Final Documentation | - | - | -
4.3 | Procurement Forms | - | - | -
4.4 | Selection Process | - | - | -
4.5 | Terrorism Financing Check | - | - | -
4.6 | Sole Sourcing | - | - | -
4.7 | Vehicle Management | - | - | -
4.8 | Travel | - | - | -
4.9 | Lease Agreement | - | - | -
4.1 | Thresholds | - | - | -
4.11 | Basis for award cost | - | - | -
4.12 | Staff Skill Set | - | - | -
4.13 | Insurance | - | - | -
| Average Score | - | - | -
5. Property Management
5.1 | Fixed asset register | - | - | -
5.2 | Tracking System | - | - | -
5.3 | Segregation of Duty | - | - | -
5.4 | Updates | - | - | -
5.5 | Disposal | - | - | -
5.6 | Storage | - | - | -
5.7 | Locked storage | - | - | -
5.8 | Property Management Policy and procedures | - | - | -
5.9 | Fixed Assets/Equipment disposal process | - | - | -
5.1 | Safekeeping/safeguarding of fixed assets | - | - | -
| Average Score | - | - | -
6. Information Technology
6.1 | IT Committee | - | - | -
6.2 | IT Plan | - | - | -
6.3 | IT Risk Mitigation | - | - | -
6.4 | Cybersecurity | - | - | -
6.5 | Access | - | - | -
6.6 | Staff terminations | - | - | -
6.7 | Data retention | - | - | -
6.8 | Error tracking system | - | - | -
6.9 | Disaster recovery | - | - | -
6.1 | Segregation of duties | - | - | -
6.11 | Back-ups | - | - | -
6.12 | Antivirus | - | - | -
6.13 | Firewall | - | - | -
6.14 | Guest network | - | - | -
6.15 | Operating system update | - | - | -
6.16 | Updating Workstations, laptops and computers | - | - | -
6.17 | Software installation and license | - | - | -
6.18 | Passwords | - | - | -
6.19 | Automatic shutdowns | - | - | -
6.2 | Licenses | - | - | -
| Average Score | - | - | -
7. Human Resources
7.1 | Fair recruitment | - | - | -
7.2 | Files for recruitment | - | - | -
7.3 | Reference and salary checks | - | - | -
7.4 | Vacancies | - | - | -
7.5 | Personnel files | - | - | -
7.6 | Orientation | - | - | -
7.7 | Career Advancement | - | - | -
7.8 | Professional development opportunities | - | - | -
7.9 | Personnel Appraisals | - | - | -
7.1 | Attrition | - | - | -
7.11 | Resignations | - | - | -
7.12 | Staff on payroll | - | - | -
7.13 | Payroll changes | - | - | -
7.14 | Payroll approval | - | - | -
7.15 | Deductions | - | - | -
7.16 | Level of efforts | - | - | -
7.17 | Organigram | - | - | -
7.18 | Expenses | - | - | -
7.19 | Staff advances | - | - | -
7.2 | Lodging | - | - | -
7.21 | Personnel Data Protection | - | - | -
7.22 | Diversity, Equality and Inclusion (DEI) | - | - | -
7.23 | Staff Wellness | - | - | -
7.24 | HR Reports | - | - | -
7.25 | Exit Interviews | - | - | -
7.26 | Staff Engagement | - | - | -
7.27 | Compensation | - | - | -
7.28 | Security & Safety | - | - | -
7.29 | Employee relations | - | - | -
7.3 | Time sheet | - | - | -
7.31 | Staff Skill Set | - | - | -
7.32 | Employee and Consultant Contracts | - | - | -
7.33 | Code of Conduct or Ethics | - | - | -
7.34 | Training on Code of Ethics | - | - | -
7.35 | Personal Identifiable Information | - | - | -
| Average Score | - | - | -
8. Monitoring and Evaluation
8.1 | M&E Unit | - | - | -
8.2 | M&E Plan | - | - | -
8.3 | Routine monitoring | - | - | -
8.4 | Databases | - | - | -
8.5 | Supervision and Data quality | - | - | -
8.6 | Data use | - | - | -
| Average Score | - | - | -
9. Gender
9.1 | Gender equality policy | - | - | -
9.2 | Gender integration training for staff | - | - | -
9.3 | Gender budgeting | - | - | -
9.4 | Gender Equality and Women's Empowerment in Mission statement | - | - | -
9.5 | Gender Focal point | - | - | -
9.6 | Gender and GBV issues are integrated/incorporated in programmatic strategies | - | - | -
9.7 | Sex-disaggregation of data on program beneficiaries | - | - | -
9.8 | Gender analysis | - | - | -
9.9 | Strategic plan for gender equality | - | - | -
9.1 | Gender roles and responsibilities | - | - | -
9.11 | Sexual Harassment and abuse Policy | - | - | -
9.12 | Gender communication | - | - | -
9.13 | Gender parity in top level leadership and technical positions | - | - | -
9.14 | LGBTG disaggregation | - | - | -
9.15 | Equal opportunity policies | - | - | -
9.16 | Family -friendly policies | - | - | -
9.17 | LGBT Policy | - | - | -
| Average Score | - | - | -
10 Governance
10.1 | Governance structure
10.2 | Board membership
10.3 | Rules
10.4 | Roles and Responsibilities
10.5 | Meetings
10.6 | Documentation
10.7 | Decision making
10.8 | Fiduciary Risk Management
10.9 | Board Evaluation
10.1 | Board and Main Governance Committee Structure
10.11 | Finance Management
10.12 | Strategic Plan
10.13 | Performance Management
10.14 | Risk Management
10.15 | Executive Leadership
10.16 | Succession Plans
Average Score
11. Subaward Management
11.1 | Subawards | - | - | -
11.2 | Subaward Manual | - | - | -
11.3 | Mechanism Types | - | - | -
11.4 | Subaward Planning | - | - | -
11.5 | Competitive Solicitation | - | - | -
11.6 | Non Competitive Solicitations | - | - | -
11.7 | Prime approvals | - | - | -
11.8 | Pre award assessment | - | - | -
11.9 | Special Award Conditions (SAC) | - | - | -
11.1 | Flow downs | - | - | -
11.11 | Budget | - | - | -
11.12 | Indirect costs | - | - | -
11.13 | Annual Workplan | - | - | -
11.14 | Subaward Reporting | - | - | -
11.15 | Capacity Strengthening | - | - | -
11.16 | Modifications | - | - | -
11.17 | Monitoring Plan | - | - | -
11.18 | Deficiencies | - | - | -
11.19 | Financial Management | - | - | -
11.2 | Inventory | - | - | -
11.21 | Site visits | - | - | -
11.22 | Close Out | - | - | -
11.23 | Evaluation of Proposals | - | - | -
11.24 | Staff Skill Set | - | - | -
| Average Score | - | - | -
12. Communication
12.1 | Communications Strategy and Goals | - | - | -
12.2 | Staff Capacity | - | - | -
12.3 | Information Management / Knowledge Management | - | - | -
12.4 | Monitoring & Evaluation of communication activities | - | - | -
12.5 | Knowledge Management and External Linkages | - | - | -
12.6 | Internal Communications and Decision Making | - | - | -
12.7 | External Communications | - | - | -
12.8 | Branding | - | - | -
12.9 | USAID Logo | - | - | -
12.1 | Marking Plan | - | - | -
12.11 | Disclaimer | - | - | -
12.12 | Exceptions | - | - | -
| Average Score | - | - | -
13. Key Populations
13.1 | Legal | - | - | -
13.2 | Governance | - | - | -
13.3 | Human Resources | - | - | -
13.4 | Organizational Sustainability | - | - | -
13.5 | Community Out reach KP | - | - | -
13.6 | Country Environment | - | - | -
| Average Score | - | - | -
14. Business Development
14.1 | Resource mobilization plan | - | - | -
14.2 | Dedicated staff | - | - | -
14.3 | Targets | - | - | -
14.4 | Proposal preparation | - | - | -
14.5 | Budget for resource mobilization | - | - | -
14.6 | Advocacy and Influence | - | - | -
14.7 | Diversified funding | - | - | -
| Average Score | - | - | -
15. Award Management
15.1 | Start Up | - | - | -
15.2 | Leadership | - | - | -
15.3 | Procurement | - | - | -
15.4 | Financial Management | - | - | -
15.5 | Monitoring | - | - | -
15.6 | Reporting | - | - | -
15.7 | Close out | - | - | -
| Average Score | - | - | -
16.Sustainability Assessment
16.1 | Legal | - | - | -
16.2 | Governance | - | - | -
16.3 | Sustainability | - | - | -
16.4 | Finance | - | - | -
16.5 | Human Resources | - | - | -
16.6 | Information Technology | - | - | -
16.7 | Gender | - | - | -
16.8 | Strategic Information | - | - | -
| Average Score | - | - | -
17. Mandatory Standard Provisions
17.1 | M1-Allowable Costs | - | - | -
17.2 | M2-Accounting, Audit and Records | - | - | -
17.3 | M3-Amendment of Award and Revision of Budget | - | - | -
17.4 | M4. Notices | - | - | -
17.5 | M5. Policies | - | - | -
17.6 | M6-USAID Eligibility Rules for Procurement of Commodities and Services | - | - | -
17.7 | M7-Title To and Use of Property | - | - | -
17.8 | M8-Submissions to the Development Experience Clearinghouse and Data Rights | - | - | -
17.9 | M9-Marking and Public Communications under USAID funded assistance. | - | - | -
17.1 | M10-Award Termination and Suspension | - | - | -
17.11 | M11-Receipient and Employee Conduct | - | - | -
17.12 | M12-Debarment and Suspension | - | - | -
17.13 | M13-Disputes and Appeals | - | - | -
17.14 | M14- Preventing Terrorist Financing | - | - | -
17.15 | M15- Trafficking of Persons | - | - | -
17.16 | M16-Voluntary Population Planning Activities - Mandatory Requirements | - | - | -
17.17 | M17-Equal Participation by Faith Based Organizations | - | - | -
17.18 | M18-Non-Discrimination | - | - | -
17.19 | M19-USAID Disability Policy - Assistance | - | - | -
17.2 | M20-Limiting Construction Activities | - | - | -
17.21 | M21-USAID Implementing Partner Notices (IPN) Portal for Assistance | - | - | -
17.22 | M22-Pilot Program for Enhancement of Grantee Employees Whistle-blower Protection | - | - | -
17.23 | M23-Submission of Datasets to the Development Data Library | - | - | -
17.24 | M24-Prohibition on Requiring Certain Internal Confidentiality Agreements or Statements | - | - | -
17.25 | M25-Child Safeguarding | - | - | -
17.26 | M26-Mandatory Disclosures | - | - | -
17.27 | M27-Non-Discrimination Against Beneficiaries (to check against M18) | - | - | -
17.28 | M28-Conflict of Interest | - | - | -
17.29 | M29. Prohibition on Certain Telecommunication and Video Surveillance Services or Equipment (July 2022) | - | - | -
| Average Score | - | - | -
18. Required as Applicable Provisions
18.1 | RAA1 Advance Payment And Refunds | - | - | -
18.2 | RAA2 Reimbursement Payment And Refunds | - | - | -
18.3 | RAA3 Indirect Costs – Negotiated Indirect Cost Rate Agreement (NICRA) | - | - | -
18.4 | RAA4 Indirect Costs – Charged As A Fixed Amount | - | - | -
18.5 | RAA5 Indirect Costs – Charged As A De Minimis | - | - | -
18.6 | RAA6 Universal Identifier And System Of Award Management | - | - | -
18.7 | RAA7 Reporting Subawards And Executive Compensation | - | - | -
18.8 | RAA8 Subawards | - | - | -
18.9 | RAA9 Travel And International Air Transportation | - | - | -
18.1 | RAA10 Ocean Shipment Of Goods | - | - | -
18.11 | RAA11 Reporting Host Government Taxes | - | - | -
18.12 | RAA12 Patent Rights | - | - | -
18.14 | RAA13 Exchange Visitors And Participating Training | - | - | -
18.15 | RAA 14 Investment Promotion | - | - | -
18.16 | RAA 15 Cost Share | - | - | -
18.17 | RAA 16 Program Income | - | - | -
18.18 | RAA17 Foreign Government Delegations To International Conferences | - | - | -
18.19 | RAA 18 Standards For Accessibility For The Disabled In USAID Assistance Awards Involving Construction For New And Renovation Construction | - | - | -
18.2 | RAA 19 Protection Of Human Research Subjects | - | - | -
18.21 | RAA 20 Statement For Implementers Of Anti-Trafficking Activities On Lack Of Support For Prostitution | - | - | -
18.22 | RAA 21 Eligibility Of Subrecipients Of Anti-Trafficking Funds | - | - | -
18.23 | RAA 22 Prohibition On The Use Of Anti-Trafficking Funds To Promote, Support, Or Advocate For The Legalization Or Practice Of Prostitution | - | - | -
18.24 | RAA 23 Voluntary Population Planning Activities – Supplemental Requirements | - | - | -
18.25 | RAA 24 Conscience Clause Implementation (Assistance) | - | - | -
18.26 | RAA 25 Condoms (Assistance) | - | - | -
18.27 | RAA 26 Prohibition On The Promotion Or Advocacy Of The Legalization Or Practice Of Prostitution Or Sex Trafficking(Assistance) | - | - | -
18.28 | RAA 27 Limitation On Subawards To Non-Local Entities | - | - | -
18.29 | RAA 28 Contract Provision For Dba Insurance Under Recipient Procurements | - | - | -
18.3 | RAA 29 Contract Award Terms And Conditions For Recipient Integrity And Performance Matters (Dec. 2022) | - | - | -
18.31 | RAA30. Never Contract with the Enemy | - | - | -
| Average Score | - | - | -
19. Environmental Mitigation and Monitoring
19.1 | Plan | - | - | -
19.2 | Project/Activity Data | - | - | -
19.3 | Organizational/Administrative Data | - | - | -
19.4 | Initial Submission | - | - | -
19.5 | Environmental conditions | - | - | -
19.6 | Workplan | - | - | -
19.7 | Corrective Action Plan | - | - | -
19.8 | Timely Annual Submissions | - | - | -
| Average Score | - | - | -

## CDP 2
ASAP II CAPACITY DEVELOPMENT PLAN
ORGANIZATON NAME
DATE OF UPDATE
DOMAIN AND CRITERIA |  | BASELINE SCORE | REASSESSMENT 1 | REASSESSMENT 2 | KEY ACTIVITIES | SUB ACTIVITIES | EXPECTED RESULTS | ORGANIZATIONAL LEAD | CAPACITY ADVISOR | TOOL USED OR DEVELOPED | START DATE | END DATE | ADD COLUMNS FOR MONTH OR QUARTERS | ORGANIZATION UPDATE | CAPACITY ADVISOR UPDATES | ASAP II INDICATOR
|  | Date: | Date: | Date:
1. Legal
1.1 | Subawards | - | - | -
1.2 | Pre-Award Questionnaire | - | - | -
1.3 | Agreement | - | - | -
1.4 | Monitoring | - | - | -
1.5 | Audit | - | - | -
1.6 | Tracking | - | - | -
1.7 | Taxes | - | - | -
1.8 | Delegation of Authority | - | - | -
1.9 | Law suits | - | - | -
| Average Score | - | - | -
2. Finance
2.1 | Budget | - | - | -
2.2 | Cost Allocation | - | - | -
2.3 | Documentation | - | - | -
2.4 | Advance payments | - | - | -
2.5 | Petty Cash | - | - | -
2.6 | Budget Variance | - | - | -
2.7 | Cash Flow Budgets | - | - | -
2.8 | Accounting System | - | - | -
2.9 | Accounting Records | - | - | -
| Average Score | - | - | -
3. Fraud
3.1 | Policy | - | - | -
3.2 | Reporting | - | - | -
3.3 | Risk assessment | - | - | -
3.4 | Training | - | - | -
3.5 | Subawards | - | - | -
3.6 | Compliance | - | - | -
3.7 | Internal controls | - | - | -
| Average Score | - | - | -
4. Procurement and Logistics
4.1 | Approval Process | - | - | -
4.2 | Final Documentation | - | - | -
4.3 | Procurement Forms | - | - | -
4.4 | Selection Process | - | - | -
4.5 | Terrorism Financing Check | - | - | -
4.6 | Sole Sourcing | - | - | -
4.7 | Vehicle Management | - | - | -
4.8 | Travel | - | - | -
4.9 | Lease Agreement | - | - | -
4.1 | Thresholds | - | - | -
4.11 | Basis for award cost | - | - | -
4.12 | Staff Skill Set | - | - | -
4.13 | Insurance | - | - | -
| Average Score | - | - | -
5. Property Management
5.1 | Fixed asset register | - | - | -
5.2 | Tracking System | - | - | -
5.3 | Segregation of Duty | - | - | -
5.4 | Updates | - | - | -
5.5 | Disposal | - | - | -
5.6 | Storage | - | - | -
5.7 | Locked storage | - | - | -
5.8 | Property Management Policy and procedures | - | - | -
5.9 | Fixed Assets/Equipment disposal process | - | - | -
5.1 | Safekeeping/safeguarding of fixed assets | - | - | -
| Average Score | - | - | -
6. Information Technology
6.1 | IT Committee | - | - | -
6.2 | IT Plan | - | - | -
6.3 | IT Risk Mitigation | - | - | -
6.4 | Cybersecurity | - | - | -
6.5 | Access | - | - | -
6.6 | Staff terminations | - | - | -
6.7 | Data retention | - | - | -
6.8 | Error tracking system | - | - | -
6.9 | Disaster recovery | - | - | -
6.1 | Segregation of duties | - | - | -
6.11 | Back-ups | - | - | -
6.12 | Antivirus | - | - | -
6.13 | Firewall | - | - | -
6.14 | Guest network | - | - | -
6.15 | Operating system update | - | - | -
6.16 | Updating Workstations, laptops and computers | - | - | -
6.17 | Software installation and license | - | - | -
6.18 | Passwords | - | - | -
6.19 | Automatic shutdowns | - | - | -
6.2 | Licenses | - | - | -
| Average Score | - | - | -
7. Human Resources
7.1 | Fair recruitment | - | - | -
7.2 | Files for recruitment | - | - | -
7.3 | Reference and salary checks | - | - | -
7.4 | Vacancies | - | - | -
7.5 | Personnel files | - | - | -
7.6 | Orientation | - | - | -
7.7 | Career Advancement | - | - | -
7.8 | Professional development opportunities | - | - | -
7.9 | Personnel Appraisals | - | - | -
7.1 | Attrition | - | - | -
7.11 | Resignations | - | - | -
7.12 | Staff on payroll | - | - | -
7.13 | Payroll changes | - | - | -
7.14 | Payroll approval | - | - | -
7.15 | Deductions | - | - | -
7.16 | Level of efforts | - | - | -
7.17 | Organigram | - | - | -
7.18 | Expenses | - | - | -
7.19 | Staff advances | - | - | -
7.2 | Lodging | - | - | -
7.21 | Personnel Data Protection | - | - | -
7.22 | Diversity, Equality and Inclusion (DEI) | - | - | -
7.23 | Staff Wellness | - | - | -
7.24 | HR Reports | - | - | -
7.25 | Exit Interviews | - | - | -
7.26 | Staff Engagement | - | - | -
7.27 | Compensation | - | - | -
7.28 | Security & Safety | - | - | -
7.29 | Employee relations | - | - | -
7.3 | Time sheet | - | - | -
7.31 | Staff Skill Set | - | - | -
7.32 | Employee and Consultant Contracts | - | - | -
7.33 | Code of Conduct or Ethics | - | - | -
7.34 | Training on Code of Ethics | - | - | -
7.35 | Personal Identifiable Information | - | - | -
| Average Score | - | - | -
8. Monitoring and Evaluation
8.1 | M&E Unit | - | - | -
8.2 | M&E Plan | - | - | -
8.3 | Routine monitoring | - | - | -
8.4 | Databases | - | - | -
8.5 | Supervision and Data quality | - | - | -
8.6 | Data use | - | - | -
| Average Score | - | - | -
9. Gender
9.1 | Gender equality policy | - | - | -
9.2 | Gender integration training for staff | - | - | -
9.3 | Gender budgeting | - | - | -
9.4 | Gender Equality and Women's Empowerment in Mission statement | - | - | -
9.5 | Gender Focal point | - | - | -
9.6 | Gender and GBV issues are integrated/incorporated in programmatic strategies | - | - | -
9.7 | Sex-disaggregation of data on program beneficiaries | - | - | -
9.8 | Gender analysis | - | - | -
9.9 | Strategic plan for gender equality | - | - | -
9.1 | Gender roles and responsibilities | - | - | -
9.11 | Sexual Harassment and abuse Policy | - | - | -
9.12 | Gender communication | - | - | -
9.13 | Gender parity in top level leadership and technical positions | - | - | -
9.14 | LGBTG disaggregation | - | - | -
9.15 | Equal opportunity policies | - | - | -
9.16 | Family -friendly policies | - | - | -
9.17 | LGBT Policy | - | - | -
| Average Score | - | - | -
10 Governance
10.1 | Governance structure
10.2 | Board membership
10.3 | Rules
10.4 | Roles and Responsibilities
10.5 | Meetings
10.6 | Documentation
10.7 | Decision making
10.8 | Fiduciary Risk Management
10.9 | Board Evaluation
10.1 | Board and Main Governance Committee Structure
10.11 | Finance Management
10.12 | Strategic Plan
10.13 | Performance Management
10.14 | Risk Management
10.15 | Executive Leadership
10.16 | Succession Plans
Average Score
11. Subaward Management
11.1 | Subawards | - | - | -
11.2 | Subaward Manual | - | - | -
11.3 | Mechanism Types | - | - | -
11.4 | Subaward Planning | - | - | -
11.5 | Competitive Solicitation | - | - | -
11.6 | Non Competitive Solicitations | - | - | -
11.7 | Prime approvals | - | - | -
11.8 | Pre award assessment | - | - | -
11.9 | Special Award Conditions (SAC) | - | - | -
11.1 | Flow downs | - | - | -
11.11 | Budget | - | - | -
11.12 | Indirect costs | - | - | -
11.13 | Annual Workplan | - | - | -
11.14 | Subaward Reporting | - | - | -
11.15 | Capacity Strengthening | - | - | -
11.16 | Modifications | - | - | -
11.17 | Monitoring Plan | - | - | -
11.18 | Deficiencies | - | - | -
11.19 | Financial Management | - | - | -
11.2 | Inventory | - | - | -
11.21 | Site visits | - | - | -
11.22 | Close Out | - | - | -
11.23 | Evaluation of Proposals | - | - | -
11.24 | Staff Skill Set | - | - | -
| Average Score | - | - | -
12. Communication
12.1 | Communications Strategy and Goals | - | - | -
12.2 | Staff Capacity | - | - | -
12.3 | Information Management / Knowledge Management | - | - | -
12.4 | Monitoring & Evaluation of communication activities | - | - | -
12.5 | Knowledge Management and External Linkages | - | - | -
12.6 | Internal Communications and Decision Making | - | - | -
12.7 | External Communications | - | - | -
12.8 | Branding | - | - | -
12.9 | USAID Logo | - | - | -
12.1 | Marking Plan | - | - | -
12.11 | Disclaimer | - | - | -
12.12 | Exceptions | - | - | -
| Average Score | - | - | -
13. Key Populations
13.1 | Legal | - | - | -
13.2 | Governance | - | - | -
13.3 | Human Resources | - | - | -
13.4 | Organizational Sustainability | - | - | -
13.5 | Community Out reach KP | - | - | -
13.6 | Country Environment | - | - | -
| Average Score | - | - | -
14. Business Development
14.1 | Resource mobilization plan | - | - | -
14.2 | Dedicated staff | - | - | -
14.3 | Targets | - | - | -
14.4 | Proposal preparation | - | - | -
14.5 | Budget for resource mobilization | - | - | -
14.6 | Advocacy and Influence | - | - | -
14.7 | Diversified funding | - | - | -
| Average Score | - | - | -
15. Award Management
15.1 | Start Up | - | - | -
15.2 | Leadership | - | - | -
15.3 | Procurement | - | - | -
15.4 | Financial Management | - | - | -
15.5 | Monitoring | - | - | -
15.6 | Reporting | - | - | -
15.7 | Close out | - | - | -
| Average Score | - | - | -
16.Sustainability Assessment
16.1 | Legal | - | - | -
16.2 | Governance | - | - | -
16.3 | Sustainability | - | - | -
16.4 | Finance | - | - | -
16.5 | Human Resources | - | - | -
16.6 | Information Technology | - | - | -
16.7 | Gender | - | - | -
16.8 | Strategic Information | - | - | -
| Average Score | - | - | -
17. Mandatory Standard Provisions
17.1 | M1-Allowable Costs | - | - | -
17.2 | M2-Accounting, Audit and Records | - | - | -
17.3 | M3-Amendment of Award and Revision of Budget | - | - | -
17.4 | M4. Notices | - | - | -
17.5 | M5. Policies | - | - | -
17.6 | M6-USAID Eligibility Rules for Procurement of Commodities and Services | - | - | -
17.7 | M7-Title To and Use of Property | - | - | -
17.8 | M8-Submissions to the Development Experience Clearinghouse and Data Rights | - | - | -
17.9 | M9-Marking and Public Communications under USAID funded assistance. | - | - | -
17.1 | M10-Award Termination and Suspension | - | - | -
17.11 | M11-Receipient and Employee Conduct | - | - | -
17.12 | M12-Debarment and Suspension | - | - | -
17.13 | M13-Disputes and Appeals | - | - | -
17.14 | M14- Preventing Terrorist Financing | - | - | -
17.15 | M15- Trafficking of Persons | - | - | -
17.16 | M16-Voluntary Population Planning Activities - Mandatory Requirements | - | - | -
17.17 | M17-Equal Participation by Faith Based Organizations | - | - | -
17.18 | M18-Non-Discrimination | - | - | -
17.19 | M19-USAID Disability Policy - Assistance | - | - | -
17.2 | M20-Limiting Construction Activities | - | - | -
17.21 | M21-USAID Implementing Partner Notices (IPN) Portal for Assistance | - | - | -
17.22 | M22-Pilot Program for Enhancement of Grantee Employees Whistle-blower Protection | - | - | -
17.23 | M23-Submission of Datasets to the Development Data Library | - | - | -
17.24 | M24-Prohibition on Requiring Certain Internal Confidentiality Agreements or Statements | - | - | -
17.25 | M25-Child Safeguarding | - | - | -
17.26 | M26-Mandatory Disclosures | - | - | -
17.27 | M27-Non-Discrimination Against Beneficiaries (to check against M18) | - | - | -
17.28 | M28-Conflict of Interest | - | - | -
17.29 | M29. Prohibition on Certain Telecommunication and Video Surveillance Services or Equipment (July 2022) | - | - | -
| Average Score | - | - | -
18. Required as Applicable Provisions
18.1 | RAA1 Advance Payment And Refunds | - | - | -
18.2 | RAA2 Reimbursement Payment And Refunds | - | - | -
18.3 | RAA3 Indirect Costs – Negotiated Indirect Cost Rate Agreement (NICRA) | - | - | -
18.4 | RAA4 Indirect Costs – Charged As A Fixed Amount | - | - | -
18.5 | RAA5 Indirect Costs – Charged As A De Minimis | - | - | -
18.6 | RAA6 Universal Identifier And System Of Award Management | - | - | -
18.7 | RAA7 Reporting Subawards And Executive Compensation | - | - | -
18.8 | RAA8 Subawards | - | - | -
18.9 | RAA9 Travel And International Air Transportation | - | - | -
18.1 | RAA10 Ocean Shipment Of Goods | - | - | -
18.11 | RAA11 Reporting Host Government Taxes | - | - | -
18.12 | RAA12 Patent Rights | - | - | -
18.14 | RAA13 Exchange Visitors And Participating Training | - | - | -
18.15 | RAA 14 Investment Promotion | - | - | -
18.16 | RAA 15 Cost Share | - | - | -
18.17 | RAA 16 Program Income | - | - | -
18.18 | RAA17 Foreign Government Delegations To International Conferences | - | - | -
18.19 | RAA 18 Standards For Accessibility For The Disabled In USAID Assistance Awards Involving Construction For New And Renovation Construction | - | - | -
18.2 | RAA 19 Protection Of Human Research Subjects | - | - | -
18.21 | RAA 20 Statement For Implementers Of Anti-Trafficking Activities On Lack Of Support For Prostitution | - | - | -
18.22 | RAA 21 Eligibility Of Subrecipients Of Anti-Trafficking Funds | - | - | -
18.23 | RAA 22 Prohibition On The Use Of Anti-Trafficking Funds To Promote, Support, Or Advocate For The Legalization Or Practice Of Prostitution | - | - | -
18.24 | RAA 23 Voluntary Population Planning Activities – Supplemental Requirements | - | - | -
18.25 | RAA 24 Conscience Clause Implementation (Assistance) | - | - | -
18.26 | RAA 25 Condoms (Assistance) | - | - | -
18.27 | RAA 26 Prohibition On The Promotion Or Advocacy Of The Legalization Or Practice Of Prostitution Or Sex Trafficking(Assistance) | - | - | -
18.28 | RAA 27 Limitation On Subawards To Non-Local Entities | - | - | -
18.29 | RAA 28 Contract Provision For Dba Insurance Under Recipient Procurements | - | - | -
18.3 | RAA 29 Contract Award Terms And Conditions For Recipient Integrity And Performance Matters (Dec. 2022) | - | - | -
18.31 | RAA30. Never Contract with the Enemy | - | - | -
| Average Score | - | - | -
19. Environmental Mitigation and Monitoring
19.1 | Plan | - | - | -
19.2 | Project/Activity Data | - | - | -
19.3 | Organizational/Administrative Data | - | - | -
19.4 | Initial Submission | - | - | -
19.5 | Environmental conditions | - | - | -
19.6 | Workplan | - | - | -
19.7 | Corrective Action Plan | - | - | -
19.8 | Timely Annual Submissions | - | - | -
| Average Score | - | - | -